## Mai 2017
Projektplan - Siemens VR
Projekttitel | Siemens VR |  |  | Datum |  | 2017-05-01 |  | A |  |  |  | Ist-Zeit (Kevin Wüstner)
Projektstart | 2017-05-01 |  |  | Version | [7 empty] | Ist-Zeit (Daniel Betschart)
Projektende | 2017-07-20 |  |  | Abteilung |  | INF | [5 empty] | Ist-Zeit (Beide)
Projektleiter | [11 empty] | Abwesenheit (Kevin Wüstner)
Firma | Siemens | [10 empty] | Abwesenheit (Daniel Betschart)
Abwesenheit (Beide)
|  | ISSUE-Nummer | SOLL-Aufwand in Stunden |  | IST- Aufwand in Stunden
[7 empty] | Mai 2017 | [36 empty] | Juni 2017 | [29 empty] | Juli 2017
[7 empty] | 1 | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 |  | 9 |  | 10 | 11 | 12 | 13 | 14 | 15 |  | 16 |  | 17 | 18 | 19 | 20 | 21 | 22 |  | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Model Issues |  |  | 51.05 |  | 40.626
Watch |  | #55 | 1.5 |  | 0.5 |  |  | 0.5
Music Remote |  | #54 | 0.6 |  | 0
Fire Extinguisher |  | #53 | 1 |  | 0
Lamps |  | #51 | 0.8 |  | 1.25 | [12 empty] | 0.75 | [15 empty] | 0.5
Carpet |  | #50 | 0.5 |  | 0
Windows |  | #49 | 0.3 |  | 0
Voltmeter |  | #48 | 1 |  | 0.166 | [21 empty] | 0.166
Microchip |  | #47 | 0.6 |  | 0.66 | [21 empty] | 0.66
Microchip Reader |  | #46 | 0.6 |  | 0
Robot |  | #45 | 3 |  | 0
Smoke Detector |  | #44 | 1.5 |  | 0
Treadmill |  | #43 | 1 |  | 0
Watertower |  | #42 | 1 |  | 0
Garagedoor |  | #41 | 1 |  | 1 | [21 empty] | 1
Tools |  | #40 | 1 |  | 1.8 |  |  |  | 1.5 | [17 empty] | 0.3
Wheels |  | #39 | 1 |  | 1 | [12 empty] | 1
Car |  | #38 | 4 |  | 3.25 | [10 empty] | 2.25 |  | 1
Printer |  | #37 | 0.6 |  | 0.1 | [9 empty] | 0.1
Keycard |  | #36 | 0.5 |  | 0.5 | [10 empty] | 0.5
Two-Axis Lever |  | #35 | 0.3 |  | 0.1 | [9 empty] | 0.1
One-Axis Lever |  | #34 | 0.3 |  | 0
Keycard Billboard |  | #33 | 1.5 |  | 0
Decoration |  | #32 | 0.5 |  | 2.5 | [11 empty] | 2.5
Office Table |  | #31 | 0.25 |  | 1 | [9 empty] | 1
Camera |  | #30 | 0.5 |  | 0.3 | [9 empty] | 0.3
Keyboard |  | #29 | 0.5 |  | 2 | [9 empty] | 2
Monitor |  | #28 | 0.3 |  | 0.25 | [11 empty] | 0.25
Computer |  | #27 | 0.5 |  | 1.25 | [9 empty] | 1.25
Utensils |  | #26 | 1.3 |  | 2.6 | [18 empty] | 1.3 |  |  | 1.3
Cupboard + High Cupboard |  | #25 | 1.3 |  | 2 | [18 empty] | 2
Counter |  | #24 | 1 |  | 1.05 | [11 empty] | 0.3 | [6 empty] | 0.75
Fridge |  | #23 | 1 |  | 0.75 | [18 empty] | 0.75
Decoration |  | #22 | 1 |  | 0.75 | [27 empty] | 0.75
Mirror Cabinet |  | #21 | 0.3 |  | 0.5 | [20 empty] | 0.5
Sink |  | #16 | 2 |  | 3.25 | [19 empty] | 2 | 1.25
Bathtub |  | #14 | 2 |  | 2.5 | [19 empty] | 2 | 0.5
Shower |  | #13 | 2 |  | 3.25 | [20 empty] | 2 | [6 empty] | 1.25
Toilet |  | #12 | 2 |  | 1.5 | [12 empty] | 0.75 | [6 empty] | 0.75
Hallstand + clothes |  | #11 | 2 |  | 0
Mirror |  | #9 | 0.25 |  | 0
Decoration |  | #8 | 1 |  | 0
Nightstand + table lamp |  | #7 | 1.1 |  | 0.8 |  |  |  | 0.5 | [6 empty] | 0.3
Bed + Pillow |  | #5 | 1.75 |  | 1.5 |  |  |  | 1.5
TV (small one, big one) |  | #4 | 0.6 |  | 0.25 | [27 empty] | 0.25
5 different plants |  | #3 | 1 |  | 0
Couch + Armchair |  | #2 | 2.2 |  | 1.3 | [10 empty] | 1.3
Table + Chair |  | #1 | 1.1 |  | 1 | [10 empty] | 1
Code Issues |  |  | 88.6 |  | 0
Sensor, Lever, Button Scripts |  | #67 | 0.6 |  | 0
Change time with a watch |  | #66 | 1.5 |  | 0
Object Stands |  | #65 | 1 |  | 0
Moveable Objects |  | #64 | 0.5 |  | 0
Open Doors by Keycard |  | #63 | 1 |  | 0
Open Doors |  | #62 | 1 |  | 0
Test with Voltmeter |  | #61 | 4 |  | 0
Connect Parts |  | #60 | 8 |  | 0
PorfessionPhase Time/Objects adjustable |  | #59 | 1 |  | 0
Connect Chip with PC |  | #58 | 1 |  | 0
Treadmill |  | #57 | 4 |  | 0
Solve code Problems |  | #20 | 12 |  | 0
Manage diary |  | #19 | 16 |  | 0
Security |  | #18 | 5 |  | 0
Sound |  | #17 | 4 |  | 0
Light |  | #15 | 16 |  | 0
Fire |  | #10 | 6 |  | 0
Water |  | #6 | 6 |  | 0
Dokumentation |  |  | 16 |  | 0
Dokumentation |  |  | 16 |  | 0
Testing |  |  | 32 |  | 0
Testing |  |  | 32 |  | 0
Übergabe |  |  | 8 |  | 0
Erklärung |  |  | 8 |  | 0
Reserve |  |  | 36.35 |  | 0
Projektende
Gesamtstunden geplant |  |  | 195.65 |  | 40.626